## Gantt Chart Template
GANTT CHART | [26 empty] | https://goo.gl/PXLbMe
| PROJECT TITLE | Investment assistant (SISTA) with recommendation system |  |  |  |  | TEAM NAME | [8 empty] | C22-275
| PROJECT MANAGER | Supriadi |  |  |  |  | DATE | [8 empty] | 10/25/22 - 11/20/22
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Persiapan Data
1.1 | Mengatasi Missing Value |  | 2022-10-25 | 2022-10-28 | 3 | 0% | bar: WEEK 1 T to WEEK 1 F
1.2 | Scaling |  | 2022-10-25 | 2022-10-28 | 3 | 0% | bar: WEEK 1 T to WEEK 1 F
1.3 | Standarisasi |  | 2022-10-25 | 2022-10-28 | 3 | 0% | bar: WEEK 1 T to WEEK 1 F
1.4 | Evaluation preprocessing |  | 2022-10-28 | 2022-10-30 | 2 | 0% | bar: WEEK 1 F
2 | Membuat Model
2.1 | Pembuatan model algoritma |  | 2022-10-30 | 2022-11-03 | 3 | 0% | bar: WEEK 2 M to WEEK 2 R
2.2 | Melatih Model |  | 2022-10-30 | 2022-11-03 | 3 | 0% | bar: WEEK 2 M to WEEK 2 R
2.3 | Evaluasi Model |  | 2022-11-03 | 2022-11-04 | 1 | 0% | bar: WEEK 2 R to WEEK 2 F
3 | Membuat Deployment
3.1 | Penerapan kesumber akses |  | 2022-11-04 | 2022-11-09 | 5 | 0% | bar: WEEK 2 F to WEEK 3 W
3.2 | Integrasi proses |  | 2022-11-07 | 2022-11-10 | 3 | 0% | bar: WEEK 3 M to WEEK 3 R
3.3 | Evaluasi Deployment |  | 2022-11-10 | 2022-11-11 | 1 | 0% | bar: WEEK 3 R to WEEK 3 F
4 | Membuat Web
4.1 | Pembuatan kerangka HTML |  | 2022-11-11 | 2022-11-13 | 2 | 0% | bar: WEEK 3 F to WEEK 4 M
4.2 | Pembuatan CSS dan JS |  | 2022-11-11 | 2022-11-16 | 5 | 0% | bar: WEEK 3 F to WEEK 4 R
4.3 | Evaluasi Pembuatan Web |  | 2022-11-17 | 2022-11-18 | 1 | 0% | bar: WEEK 4 R to WEEK 4 F
5 | Monitoring
5.1 | Evaluasi |  | 2022-11-18 | 2022-11-20 | 2 | 0% | bar: WEEK 4 F